## Task & Timeline
| Sauce & Spoon Project Plan | Notes
| Task |  | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE
[8 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3
ID | [7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Milestone 1: Tablet and vendors selected
1.1 | Research tablet system options |  |  |  | 1 day | Seydou
1.2 | Connect Suace & Spoon with terrific Tablets for branding |  |  |  | 4 hours | Seydou
1.3 | Generate quotes and review costs for tablets and electrician vendors |  |  |  | 4 hours | Seydou
1.4 | Test out tablet systems |  |  |  | 3 days | Peta
1.5 | Choose a tablet system and order tablets |  |  |  | 2 days | Peta
1.6 | Create contracts and statements of work for vendors |  |  |  | 3 days | Peta
2 | Milestone 2: Tablets working with proper features
2.1 | Wait for tablets to arrive | Seydou projected 7-10 days shipping timeline, 3-4 hours to integrate the POS systems -has to ship from further away warehouse, adds a few days |  |  | 10 days | Peta
2.2 | Reorder any broken tablets |  |  |  | 1 day | Peta
2.3 | Make sure tablets compatible with current POS software | depends on if we have 3.0 or older, I think ours might be older |  |  | 3 days | Deanna
2.4 | Meet with staff on incoming tablet sytem and any features that might affect tipping and payment |  |  |  | 1 hour | Deanna
2.5 | Decide on and mock upmenu items to promote on system and link coupons | still waiting, Carter unpredicatble |  |  | 1 week | Carter
2.6 | Schedule both smaller and larger training sessions |  |  |  | 4 hours | Peta
2.7 | Work with Tablet vendor on custom branding, design, and uploading menus to tablets | vendor has done this many times, received estimate from mult. team members |  |  | 4 hours | Seydou
2.8 | Install Cross-promotional feature on tablets that pair menu items and add-ons | never done before, try and work with vendor or Seydou |  |  | 2 days | Peta
3 | Milestone 3: Staff trained on tablet system
3.1 | Test tablets working and that staff has credentials to access | do day of pre-training |  |  | 4 hours | Peta
3.2 | Pre-training meeting to introduce tablets and changes to staff before training them on the tablets | low risk as just presenting tablets and plan (each training on dif day) |  |  | 1 hour | Peta
3.3 | Small training of PjM, GMs, and Dir. of Ops on tablets by Seydou | never done before, but used to trainings |  |  | 4 hours | Seydou
3.4 | Larger trainign of FOH and BOH workers on tablets by GMs, PjM | never done before |  |  | 4 hours | Alex
4 | Milestone 4: Tablets installed and ready for launch
4.1 | Create troubleshoot/support plan for launch day |  |  |  | 4 days | Peta
4.2 | Install tablets at bars in Downtown and North Area locations (wiring) | needs 2 half days at each location to minimize business impact |  |  | 4 days | Peta
4.3 | Test run tablet system in with friends and family |  |  |  | 4 hours | Deanna
4.4 | Implement Customer satisfaction survey on tablets |  |  |  | 1 day | Deanna
4.5 | Launch day |  | April 29th (F) | April 29th (F) | 1 day | Peta
4.6 | Upgrade tablets to newer system (swa out plugs) | simple, only delay is if tablets arirve broken or unforseen power outage |  |  | 1 day | Deanna

## Task Brainstorm
Task Brainstorm
Task | Notes | Est. Duration | Optemisstic | Pesimitic | Most Likely | Confidence (H,M,L)
Order tablets | - shipping+ ordering takes a week , delayed shipping 2-3 days, expedited if broken | 10 days
Find vendors
Connect tablets to integrated POS system | - find out what sfotware version, then seydou needs to add some code to pos, then reboot | 3 days |  |  |  | l
mockup for menus
train managers | - 10 days to fully train everyone, |  | 10 | 21 | 14
trainings for staff
wiring tablets | - electrician for both locations in 2 bus days (16hrs), team says (4 days) 2 half days at each location
install new signage

## Quality & Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Quality Standards Category | Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer Satisfaction | Avg ticket time is 8 minutes for appetizers and 12-15 minutes for entrees. | customer satisfaction rate with using tablet, turnover rate before and after | The average ticket time is 8 minutes for appetizers and 12-15 minutes for entrees. | FALSE
Customer Satisfaction | A one-minute or less average checkout time. | Are the tablets saving time? | Checkout time for guests is 1 minute or less. | FALSE
Customer Satisfaction | Less than 5% of customers who use tablets report technical issues each week. | What type of technical issues? How long has this been happenig? is there a specific thing that is being reported? Do the tablets work as expected? | Less than 5% of customers who use tbalets report technical issues each week. | FALSE
Customer Satisfaction | 98% tablet order accuracy. | Are the customers receiving the correct orders? | 98% of customers receive the correct order. | FALSE
Customer Satisfaction | Less than 10 minute average wait time for seating. | Does the tablets have direct impact | The average wait time goes down. | FALSE

## Survey Questions
Survey Questions
Criteria/DescriptionCriteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Average ticket time is 8 minutes for appetizers and 12-15 minutes for entrees. | Are the customers having a better dining experience with the tablets? | The average ticket time is 8 minutes for appetizers and 12-15 minutes for entrees. | How long did your entire dining experience take? Please use your best judegement. | Multiple choice | Less than 30 minutes | Between 30 and 45 minutes | Between 45 minutes to 1 hour | Between 1 hour and 1.5 hours | More than 1.5 hours
A five-minute or less average checkout time. | Are the tablets saving time? | Checkout time for guests is 1 minute or less. | How easy was the tablet for you to use? | Multiple choice | Extremely Difficult | Difficult | Nuetral | Easy | Extremely easy
Less than 5% of customers who use tbalets report technical issues each week. | Do the tablets work as expected? | Less than 5% of customers who use tablets report technical issues each week. | Did everyone in your party receive the correct order? | Yes/No | Yes | No
98% tablet order accuracy. | Are the customers receiving the correct orders? | 98% of customers receive the correct order. | How long did you wait between ordering your entree and it's arrival. Please use your best judgement. | Multiple choice | Less than 5 minutes | Between 5 and 10 minutes | Between 10 and 15 minutes | More than 15 minutes | Our order never arrived. We had to ask someone.
Less than 10 minute average wait time for seating. | How long are customers waiting to be seated? |  | How long did you wait in the lobby before being seated? | Multiple choice | 5 minutes or less | Between 5 and 10 minutes | Between 10 and 30 minutes | more than 30 minutes | I had a reservation

## Retrospective
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | went well | rating tablet experince | - 72% had good to great experinece
Seydou | needs improvment | installing tablet took longer than expected
zane | went well | tickets were easy to get & keep track of
customers | needs improvment | easy tablet navigation was | 48% said fairly/very easy
customers | needs improvment
customers | went well | signed up for news paper | 78% sign up from tablet
Larissa | needs improvment | orders being sent back | said in retrospective meeting
Seydou | went well | technical issues / integration/ maintence but easy to idenitgy issue | said in retrospective meeting
larissa | needs improvment | lack of understanding from FOH + BOH needs more training | said in retrospective meeting
customers | needs improvment | only 72% orders were prepared correctly, the goal was 98% | customer survey from tbalet
peta | needs improvment | table turntimes were not decreasing | said in retrospective meeting